## RTM
Requirements Traceability Matrix (RTM)
Graduation 1 baseline · 20 functional requirements · evidence recorded as of 17 October 2026
Test columns map to planned case IDs in CASE-SHEETS (BloodBank_Test_Case_Sheets.docx). The IDs are definitions, not pass results; verified runs are recorded separately in RUN-17OCT.
ID | Title | Associated Dependency | SRS Section | Detailed Design | Coding | Component Test | Integration Test | System Test | Acceptance Test | Change Request No
FR-01 | Multi-bank and hospital platform | FR-02; FR-04; FR-07; FR-09 | REQ / FR-01 | API §6 / ORG-01–10 ERD: banks, hospitals, users ORG-UML: UC-01; SQ-01; AD-01 | Implemented | TC-01-CT | TC-01-IT | TC-01-ST | TC-01-AT
FR-02 | Authentication and role access | FR-01; business-module policies; FR-17 | REQ / FR-02 | API §5 / AUTH-01–06 ERD: users, roles ID-UML: UC-02; SQ-02; AD-02 | Implemented | TC-02-CT | TC-02-IT | TC-02-ST | TC-02-AT
FR-03 | Donor registration | FR-01; FR-02; FR-04 | REQ / FR-03 | API §7 / DONOR-01–04 ERD: donors, donations | Not Yet | TC-03-CT | TC-03-IT | TC-03-ST | TC-03-AT
FR-04 | Donation recording and eligibility | FR-01–03; FR-14 | REQ / FR-04 | API §7 / DON-01–11 ERD: donations | Not Yet | TC-04-CT | TC-04-IT | TC-04-ST | TC-04-AT
FR-05 | Screening results and donor notification | FR-02; FR-04; FR-08; FR-14; email provider | REQ / FR-05 | API §8 / LAB-01–09 ERD: screening_results, screening_decisions, donor_notifications | Not Yet | TC-05-CT | TC-05-IT | TC-05-ST | TC-05-AT
FR-06 | Component creation and calculated expiry | FR-04; FR-05; FR-07; FR-19 | REQ / FR-06 | API §9 / INV-03 ERD: donations, components | Not Yet | TC-06-CT | TC-06-IT | TC-06-ST | TC-06-AT
FR-07 | Inventory tracking | FR-02; FR-05; FR-06; FR-08; FR-18; FR-19 | REQ / FR-07 | API §9 / INV-01–05 ERD: components | Not Yet | TC-07-CT | TC-07-IT | TC-07-ST | TC-07-AT
FR-08 | Inventory reservation controls | FR-05–07; FR-09; FR-10; FR-13; FR-19 | REQ / FR-08 | API §11 / SRC-03; §10 / REQ-07,09 ERD: reservations, components, hospital_requests | Not Yet | TC-08-CT | TC-08-IT | TC-08-ST | TC-08-AT
FR-09 | Complete hospital request creation | FR-01; FR-02; FR-10 | REQ / FR-09 | API §10 / PAT-01,02; REQ-04 ERD: patients, hospital_requests | Not Yet | TC-09-CT | TC-09-IT | TC-09-ST | TC-09-AT
FR-10 | Request status tracking | FR-09; FR-08; FR-13; FR-18; FR-19 | REQ / FR-10 | API §10 / REQ-01–08 ERD: hospital_requests, request_status_events | Not Yet | TC-10-CT | TC-10-IT | TC-10-ST | TC-10-AT
FR-11 | Exact specification source search | FR-01; FR-05–09; FR-12 | REQ / FR-11 | API §11 / SRC-01 ERD: components, banks, hospital_requests | Not Yet | TC-11-CT | TC-11-IT | TC-11-ST | TC-11-AT
FR-12 | Single nearest exact-match bank | FR-01; FR-09; FR-11 | REQ / FR-12 | API §11 / SRC-01,02 ERD: banks, hospitals, components | Not Yet | TC-12-CT | TC-12-IT | TC-12-ST | TC-12-AT
FR-13 | Staff allocation confirmation | FR-02; FR-08; FR-10–12; FR-18 | REQ / FR-13 | API §11 / SRC-02,03 ERD: reservations, components | Not Yet | TC-13-CT | TC-13-IT | TC-13-ST | TC-13-AT
FR-14 | End-to-end traceability | FR-02; FR-03–10; FR-13; FR-18; FR-19 | REQ / FR-14 | API §12.1 / TRACE-01–04 ERD: audit_events + record chain | Not Yet | TC-14-CT | TC-14-IT | TC-14-ST | TC-14-AT
FR-15 | Operational reports | FR-04; FR-07; FR-10; FR-14; FR-18; FR-19 | REQ / FR-15 | API §12.2 / RPT-01–04 ERD: source entities in ERD | Not Yet | TC-15-CT | TC-15-IT | TC-15-ST | TC-15-AT
FR-16 | Demand forecasting | FR-02; FR-09; FR-10; Python service | REQ / FR-16 | API §13 / FC-01–04; AI-01,02 ERD: forecast_runs, forecast_points | Not Yet | TC-16-CT | TC-16-IT | TC-16-ST | TC-16-AT
FR-17 | Staff account management | FR-01; FR-02; FR-14 | REQ / FR-17 | API §5 / AUTH-07–10 ERD: users, roles, user_status_events ID-UML: UC-02; SQ-02; AD-02 | Implemented | TC-17-CT | TC-17-IT | TC-17-ST | TC-17-AT
FR-18 | Component issuing and fulfillment | FR-02; FR-08; FR-10; FR-13; FR-14; FR-19 | REQ / FR-18 | API §10 / REQ-10–12 ERD: issue_records, reservations, components | Not Yet | TC-18-CT | TC-18-IT | TC-18-ST | TC-18-AT
FR-19 | Component expiry and disposal controls | FR-06–08; FR-10; FR-14; FR-18 | REQ / FR-19 | API §9 / INV-01,06,07 ERD: disposal_records, components | Not Yet | TC-19-CT | TC-19-IT | TC-19-ST | TC-19-AT
FR-20 | Dashboard and data export | FR-07; FR-10; FR-16; FR-15 | REQ / FR-20 | API §12.3 / VIEW-01; CSV-01–03 ERD: source entities in ERD | Not Yet | TC-20-CT | TC-20-IT | TC-20-ST | TC-20-AT

## Column Guide
RTM column guide
Column | What it records | How to complete it
ID | Stable identifier for one functional requirement. | Use the FR number from the approved requirements baseline.
Title | Short English name of the requirement. | Keep it aligned with the SRS heading.
Associated Dependency | Other requirements or external services needed by this requirement. | List explicit dependencies from the SRS; dependency does not mean implementation is finished.
SRS Section | Where the requirement and its acceptance criteria are specified. | Point to the FR section in REQ; preserve the same ID as the baseline.
Detailed Design | More specific design: API contract, ERD entities, and completed UML drawings. | Use source codes and section IDs; API is a proposed contract and ERD is a design, not deployed code.
Coding | Whether the main workflow has operational code. | Implemented = operational main workflow exists; Not Yet = absent or only partial groundwork. This does not certify every acceptance criterion.
Component Test | Planned component case ID for this requirement. | Use TC-xx-CT from CASE-SHEETS. The ID links to a case definition, not a test file or passed result.
Integration Test | Planned integration case ID for this requirement. | Use TC-xx-IT from CASE-SHEETS. Record actual run evidence separately.
System Test | Planned system case ID for this requirement. | Use TC-xx-ST from CASE-SHEETS. The case remains Planned until executed and evidenced.
Acceptance Test | Planned acceptance case ID for this requirement. | Use TC-xx-AT from CASE-SHEETS. Reviewer sign-off and evidence are required before a pass claim.
Change Request No | Approved change request that modifies the requirement. | Leave blank unless a change request identifier exists; the SRS revision history is not a CR number.
Source codes appear in the Source Register. A blank RTM cell means no matching artifact was found in the reviewed repository.

## Source Register
Source register
Code | Artifact | Repository location | Scope / caution
REQ | Approved SRS and acceptance criteria | docs/BloodBank_Requirements.docx | Authoritative FR-01–FR-20 baseline; revised 15 October 2026
ARCH | Software architecture | docs/Software_Architecture.docx | Planned module boundaries, runtime interactions, and data architecture
ARCH-DIAG | Architecture diagrams | docs/architecture/context.mmd; application.mmd; modules.mmd; deployment.mmd | Design diagrams, not proof of deployment
ERD | Master entity relationship diagram | docs/erd/mermaid_only/main_erd.mmd | Compact planned data model; detailed fields are in REQ/API
API | Backend API reference | docs/BACKEND_API_REFERENCE.md | Proposed implementation contract; §15 maps every FR to endpoint IDs
ORG-UML | Organization UML drawings | docs/uml/Use Case/UC-01-Organizations.puml; docs/uml/Sequence/SQ-01-MaintainOrg.puml; docs/uml/Activity/AD-01-MaintainOrg.puml | Completed source drawings for FR-01
ID-UML | Identity UML drawings | docs/uml/Use Case/UC-02-Identity.puml; docs/uml/Sequence/SQ-02-Login.puml; docs/uml/Activity/AD-02-AccessCheck.puml | Completed source drawings for FR-02/FR-17
ORG-CODE | Organization implementation | backend/Modules/Organizations/app/Models/; backend/Modules/Organizations/database/migrations/; backend/Modules/Organizations/database/seeders/ | Models, migrations and seed data found; no organization API controller
ID-CODE | Identity implementation | backend/Modules/Identity/app/Http/; backend/Modules/Identity/routes/api.php; backend/Modules/Identity/database/; frontend/src/App.jsx | Session and staff management routes/controllers plus login UI
ORG-TEST | Organization feature tests | backend/Modules/Organizations/tests/Feature/OrganizationRecordsTest.php | 6/6 tests, 20 assertions passed on 17 October 2026; partial FR-01 model and seed coverage. See RUN-17OCT.
ID-TEST | Identity feature tests | backend/Modules/Identity/tests/Feature/AuthenticationTest.php; backend/Modules/Identity/tests/Feature/UserManagementTest.php | 19/19 tests, 154 assertions passed on 17 October 2026; partial FR-02 and FR-17 coverage. See RUN-17OCT.
UI-TEST | Frontend helper and API client tests | frontend/src/lib/access.test.js; frontend/src/lib/api.test.js | 6/6 Node tests passed on 17 October 2026 (4 access, 2 API client). No browser-level system test. See RUN-17OCT.
OPENAPI | Current OpenAPI definition | docs/openapi.yaml | Currently covers identity and health endpoints; not all proposed API routes
TEST-PLAN | English test plan and case catalogue | docs/TEST_PLAN_AND_CASES.md | Planned cases only; not execution or acceptance evidence.
CASE-SHEETS | Detailed English test case sheets | docs/BloodBank_Test_Case_Sheets.docx | 80 FR-linked cases plus seven shared checks; all results remain Not executed until recorded.
TEST-DOC | Test strategy and current test inventory | docs/BloodBank_Test_Documentation.docx | Explains plan, implemented tests, results and gaps; case sheets remain planned records.
RUN-17OCT | Test execution record, 17 October 2026 | docs/TEST_EXECUTION_2026-10-17.md | Commands and observed results for backend and frontend runs; partial evidence only.

## Test Catalogue
Test ID | Requirement | AC scope | Level | Test scenario / expected focus | Status | Definition
TC-01-CT | FR-01 | AC-01.1–3 | Component | Organization ownership and active-state rules | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-01-IT | FR-01 | AC-01.1–3 | Integration | Admin crud; wrong organization denied; record bank/hospital fks persist | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-01-ST | FR-01 | AC-01.1–3 | System | Admin manages two banks/two hospitals and staff see allowed records | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-01-AT | FR-01 | AC-01.1–3 | Acceptance | Reviewer verifies organization list, identity, ownership and deactivation | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-02-CT | FR-02 | AC-02.1–4 | Component | Role-to-navigation and permission mapping, unknown role fails closed | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-02-IT | FR-02 | AC-02.1–4 | Integration | Login/logout, hashed password, inactive user, expired token, route policy and scope denial | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-02-ST | FR-02 | AC-02.1–4 | System | Log in as each role, confirm allowed view and server rejection of forbidden url/action | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-02-AT | FR-02 | AC-02.1–4 | Acceptance | Reviewer checks access matrix and session behavior | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-03-CT | FR-03 | AC-03.1–3 | Component | Donor identity/email validation and unknown group representation | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-03-IT | FR-03 | AC-03.1–3 | Integration | Create/update/history; duplicate id rejection; cross-bank read denied | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-03-ST | FR-03 | AC-03.1–3 | System | Register donor and find all linked donation attempts in history | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-03-AT | FR-03 | AC-03.1–3 | Acceptance | Reviewer checks profile, verification state and bank scope | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-04-CT | FR-04 | AC-04.1–5 | Component | Eligibility, collection timestamps and independent progress transitions | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-04-IT | FR-04 | AC-04.1–5 | Integration | Register/assess/collect; deferred donor blocked; failed collection produces no components; audit retained | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-04-ST | FR-04 | AC-04.1–5 | System | Staff record eligible and failed attempts; verify different outcomes | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-04-AT | FR-04 | AC-04.1–5 | Acceptance | Reviewer checks original donation id, collection and processing states | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-05-CT | FR-05 | AC-05.1–4 | Component | Required-test completion and duplicate rejection-notification key | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-05-IT | FR-05 | AC-05.1–4 | Integration | Pending/rejected results block release; correction audit; one queued email; failure/retry retains rejection | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-05-ST | FR-05 | AC-05.1–4 | System | Laboratory rejects donation, reservation invalidates, mail sink receives one follow-up | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-05-AT | FR-05 | AC-05.1–4 | Acceptance | Reviewer checks decisions, history and delivery-status meaning | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-06-CT | FR-06 | AC-06.1–5 | Component | Expiry calculation from collection completion, policy version and missing configuration | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-06-IT | FR-06 | AC-06.1–5 | Integration | Create one physical component; incomplete collection and absent shelf life rejected; old expiry unchanged after policy edit | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-06-ST | FR-06 | AC-06.1–5 | System | Processing screen shows applied expiry and blocked invalid creation | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-06-AT | FR-06 | AC-06.1–5 | Acceptance | Reviewer checks calculation against approved demo policy | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-07-CT | FR-07 | AC-07.1–3 | Component | Availability predicate and one-container-one-unit totals | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-07-IT | FR-07 | AC-07.1–3 | Integration | Bank/type/group/status filters; excluded states absent from available count | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-07-ST | FR-07 | AC-07.1–3 | System | Inventory filters and detail match seeded components | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-07-AT | FR-07 | AC-07.1–3 | Acceptance | Reviewer reconciles list and available total | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-08-CT | FR-08 | AC-08.1–3 | Component | Reservation eligibility and full-quantity selection | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-08-IT | FR-08 | AC-08.1–3 | Integration | Atomic reserve/cancel/invalidate; repeat and competing requests never share a component | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-08-ST | FR-08 | AC-08.1–3 | System | Two requests compete; one obtains all units, other sees clear refusal | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-08-AT | FR-08 | AC-08.1–3 | Acceptance | Reviewer checks no partial stock loss and release after cancel | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-09-CT | FR-09 | AC-09.1–5 | Component | Conditional patient fields, positive units, date and unknown/not-applicable rules | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-09-IT | FR-09 | AC-09.1–5 | Integration | Full valid payload persists snapshots; invalid/missing values rejected; hospital derived from actor | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-09-ST | FR-09 | AC-09.1–5 | System | Hospital creates request, sees pending, then corrects form errors | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-09-AT | FR-09 | AC-09.1–5 | Acceptance | Reviewer checks required clinical/administrative fields and unit meaning | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-10-CT | FR-10 | AC-10.1–3 | Component | Request transition table and terminal-state protection | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-10-IT | FR-10 | AC-10.1–3 | Integration | Accept/reject/cancel/reserve/fulfill; invalidation returns accepted; status events stored | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-10-ST | FR-10 | AC-10.1–3 | System | Hospital and bank see consistent request history after each step | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-10-AT | FR-10 | AC-10.1–3 | Acceptance | Reviewer walks allowed and forbidden transitions | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-11-CT | FR-11 | AC-11.1–4 | Component | Exact type, abo, rh and required attributes; no substitutions | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-11-IT | FR-11 | AC-11.1–4 | Integration | Filter unavailable units, require whole quantity at one bank, no candidate list exposed | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-11-ST | FR-11 | AC-11.1–4 | System | Search shows match/no match without changing inventory | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-11-AT | FR-11 | AC-11.1–4 | Acceptance | Reviewer checks exact matching against known inventory | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-12-CT | FR-12 | AC-12.1–4 | Component | Haversine distance, units, tie-break, invalid coordinates | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-12-IT | FR-12 | AC-12.1–4 | Integration | Only nearest qualifying bank returned; missing coordinates block search publication | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-12-ST | FR-12 | AC-12.1–4 | System | Same inputs repeatedly show one bank/distance; no-match state is clear | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-12-AT | FR-12 | AC-12.1–4 | Acceptance | Reviewer checks known-distance fixture and stable tie | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-13-CT | FR-13 | AC-13.1–3 | Component | Confirmation recheck of source, quantity and eligibility | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-13-IT | FR-13 | AC-13.1–3 | Integration | Authorized source confirms; stale or changed stock rejects without partial reservation | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-13-ST | FR-13 | AC-13.1–3 | System | Staff review identifiers/distance then confirm; stale case displays refusal | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-13-AT | FR-13 | AC-13.1–3 | Acceptance | Reviewer checks approval boundary and atomic result | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-14-CT | FR-14 | AC-14.1–3 | Component | Event redaction and trace-link formatting | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-14-IT | FR-14 | AC-14.1–3 | Integration | Component-to-donor/request and request-to-components trace; correction/cancellation events immutable and scoped | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-14-ST | FR-14 | AC-14.1–3 | System | Authorized roles trace both directions; restricted role sees redacted details | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-14-AT | FR-14 | AC-14.1–3 | Acceptance | Reviewer audits a seeded component's complete chain | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-15-CT | FR-15 | AC-15.1–3 | Component | Report aggregation and zero-result formatting | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-15-IT | FR-15 | AC-15.1–3 | Integration | Known fixture totals, date/bank filters, denied scope and read-only query | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-15-ST | FR-15 | AC-15.1–3 | System | Report ui totals reconcile to seeded records; empty state visible | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-15-AT | FR-15 | AC-15.1–3 | Acceptance | Reviewer validates totals against manual fixture sheet | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-16-CT | FR-16 | AC-16.1–5 | Component | Demand-series extraction, nonnegative output and horizon validation | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-16-IT | FR-16 | AC-16.1–5 | Integration | Job/request permissions, versioned stored points, timeout/failure, no future-data leakage | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-16-ST | FR-16 | AC-16.1–5 | System | Authorized bank views run and points; other bank denied | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-16-AT | FR-16 | AC-16.1–5 | Acceptance | Reviewer approves target definition and checks backtest/baseline evidence | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-17-CT | FR-17 | AC-17.1–4 | Component | Valid role/organization combinations and bank-admin allowed-role list | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-17-IT | FR-17 | AC-17.1–4 | Integration | Admin create/edit/deactivate; bank-admin same-bank limited role change; token invalidation and audit | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-17-ST | FR-17 | AC-17.1–4 | System | Staff-management ui demonstrates allowed and denied edits | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-17-AT | FR-17 | AC-17.1–4 | Acceptance | Reviewer checks account lifecycle and assignment restrictions | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-18-CT | FR-18 | AC-18.1–4 | Component | Issue eligibility and complete reserved-quantity rule | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-18-IT | FR-18 | AC-18.1–4 | Integration | Issue transaction updates request/components/reservations together; duplicate/wrong-source/expired issue rejected | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-18-ST | FR-18 | AC-18.1–4 | System | Bank issues units; fulfilled request traces issued containers; search excludes them | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-18-AT | FR-18 | AC-18.1–4 | Acceptance | Reviewer verifies issued means source-bank issue only | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-19-CT | FR-19 | AC-19.1–3 | Component | Expires-at-now boundary and disposal transition | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-19-IT | FR-19 | AC-19.1–3 | Integration | Expired stock excluded before job; disposal audit; active reservation invalidated atomically | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-19-ST | FR-19 | AC-19.1–3 | System | Expiry/disposal changes stock and request state; repeat disposal refused | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-19-AT | FR-19 | AC-19.1–3 | Acceptance | Reviewer checks time boundary and disposal evidence | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-20-CT | FR-20 | AC-20.1–3 | Component | Dashboard count and csv cell escaping rules | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-20-IT | FR-20 | AC-20.1–3 | Integration | Figures reconcile; filtered csv columns, scope, escaping and empty export | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-20-ST | FR-20 | AC-20.1–3 | System | Dashboard/export display selected filters and downloadable safe data | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-20-AT | FR-20 | AC-20.1–3 | Acceptance | Reviewer compares dashboard, lists, forecast and csv | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-X-SEC | FR-02 and every protected FR | linked access ACs | Security | Authorization and sensitive-data boundaries | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-X-CON | FR-08, FR-13 and FR-18 | AC-08.1–3; AC-13.2–3; AC-18.1–3 | Concurrency | Competing reservation and issue transactions | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-X-API | All implemented API FRs | approved API contract | Contract | OpenAPI response and error contract | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-X-ACC | All user-interface FRs | linked usability ACs | Accessibility | Keyboard and accessible-label workflow | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-X-PERF | FR-07, FR-11, FR-15, FR-16 and FR-20 | agreed performance targets | Performance | API latency, query count and frontend performance | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-X-REC | FR-05, FR-08, FR-16 and FR-18 | linked failure-handling ACs | Recovery | Worker, service and transaction failure recovery | Planned | docs/BloodBank_Test_Case_Sheets.docx
TC-X-AI | FR-16 | AC-16.1–5 | Forecast evaluation | Chronological holdout and leakage check | Planned | docs/BloodBank_Test_Case_Sheets.docx